## Valu frnt page
BILL OF QUANTITIES
PROPOSSED HOUSE FOR MR. S.M.C.S. SIRIWARDANA
AT
ASSMT NO. 48/14, WIDURUWANA MAWATHA, SUBADRAMA ROAD, NUGEGODA.

## BOQ
BILL OF QUANTITIES
PROPOSED HOUSE FOR MR. S.M.C.S. SIRIWARDANA
AT ASSMT NO. 48/14, WIDURUWANA MAWATHA, SUBADRARAMA ROAD, NUGEGODA.
Item | Description | Qty | Unit | Rate | Amount
# |  |  |  | Rs. | Rs.
BILL NO. 01- PRELIMINARIES & DEMOLITION WORK
A- PRELIMINARIES
A | Allow for Setting out of work, temporary stores and labour hut facilities | 1 | Item | Lump Sum | 50000
B | Allow for temporary electricity and water connection | 1 | Item | Lump Sum | 35000
| Total Carried to Collection |  |  |  | 85000
B- DEMOLITION WORK
C | Demolition of existing house and cart away the debris within 10km | 1 | Item | Lump Sum | 480000
D | Demolition of existing boundary wall and cart away the debris within 10km | 1 | Item | Lump Sum | 60000
| Total Bill No. 01- Carried to Summary |  |  |  | 540000
COLLECTION - BILL NO. 01
| A- PRELIMINARIES |  |  |  | 85000
| B- DEMOLITION WORK |  |  |  | 540000
| Total Bill No. 01- Carried to Summary |  |  |  | 625000
BILL NO. 02- SUBSTRUCTURE
C- EXCAVATION AND EARTH WORK
A | Excavation for columns/ Staircase foundation | 8 | Cube | 3950 | 31600
B | Excavation for wall/ Boundary Wall foundation | 7.8 | Cube | 3660 | 28548
C | Well compacted, approved imported earth filling, | 20.3 | Cube | 5700 | 115710
| Total Carried to Collection |  |  |  | 175858
D- CONCRETE WORK
POURED CONCRETE
Insitu plain, poured and vibrated ordinary Portland cement concrete grade C15/20 as specified
D | 2" thk. concrete under columns/Staircase base | 2.8 | Sqr. | 6640 | 18592
E | 2" thk. concrete under rubble work | 2.3 | Sqr. | 6640 | 15272
F | 3" thk. Concrete floor slab | 13 | Sqr. | 9910 | 128830
Reinforced, poured and vibrated ordinary Portland cement concrete grade C25/20
column sectional areas and beams and slabs up to GF
G | columns/Staircase base | 2.4 | Cube | 40480 | 97152
H | column/Staircase shaft | 0.8 | Cube | 40480 | 32384
J | 12" x 4" plinth beams | 1.1 | Cube | 40480 | 44528
REINFORCEMENT
High yield deformed steel bar reinforcement yield stress not less than 460N/mm2
K | columns/Staircase base | 984 | Kg | 200 | 196800
| Total C/F |  |  |  | 533558
| Total B/F |  |  |  | 533558
REINFORCEMENT Cont.d
High yield deformed steel bar reinforcement yield stress not less than 460N/mm2
A | Columns up to plinth beam level | 400 | Kg | 200 | 80000
B | Plinth beams | 297 | Kg | 200 | 59400
FORMWORK
Formwork to give 'as struck' finish
| Column base and column shaft up to plinth level | 5.8 | Sqr. | 14795 | 85811
| Plinth beams | 1.1 | Sqr. | 14795 | 16274.5
| Total Carried to Collection |  |  |  | 775043.5
E- MASONRY WORK
| Random rubble masonry in cement and sand 1:5 mix in wall foundation. | 11 | Cube | 30196 | 332156
| Total Carried to Collection |  |  |  | 332156
F- ASPHALT WORK
| Supply and lay 1000 gauge polythene sheet | 13 | Sqr. | 1183 | 15379
Damp Proof Course
| Applying 2 coat of DPC tar for Ground Wall Foundation | 2.6 | Sqr. | 3766 | 9791.6
| Total Carried to Collection |  |  |  | 25170.6
COLLECTION - BILL NO. 02
BILL NO. 02- SUBSTRUCTURE
| C- EXCAVATION AND EARTH WORK |  |  |  | 175858
| D- CONCRETE WORK |  |  |  | 775043.5
| E- MASONRY WORK |  |  |  | 332156
| F- ASPHALT WORK |  |  |  | 25170.6
| Total Bill No. 02- Carried to Summary |  |  |  | 1308228.1
BILL NO. 03- SUPERSTRUCTURE
A- CONCRETE WORK
POURED CONCRETE
Insitu plain, poured and vibrated ordinary Portland cement concrete grade C15/20 as specified
column sectional areas and beams and slabs from Ground floor to First Floor Level
A | columns up to first floor slab level | 1.2 | Cube | 41998 | 50397.6
B | Slab beams at first floor slab level | 1.4 | Cube | 41998 | 58797.2
C | first floor slab | 7.7 | Cube | 41998 | 323384.6
D | stair case from Ground floor to First Floor Level | 0.6 | Cube | 41998 | 25198.8
E | 4.5 " x 6" Lintels reinforced with 02 nos 10mm | 0 | Ft. | 1320 | Deleted
F | 9 " x 6" Lintels reinforced with 04 nos 10mm | 0 | Ft. | 2290 | Deleted
column sectional areas and beams and slabs from First floor to 2nd Floor Level and roof level
G | columns up to 2nd floor slab level | 0.8 | Cube | 43010 | 34408
H | Slab beams at 2nd floor slab level | 3.25 | Cube | 43010 | 139782.5
G | 2nd floor slab | 4.4 | Cube | 43010 | 189244
H | Columns up to roof level | 0.8 | Cube | 43010 | 34408
J | stair case from First floor to Second Floor Level | 0.6 | Cube | 43010 | 25806
K | 4.5 " x 6" Lintels reinforced with 02 nos 10mm in FFL | 8 | Ft. | 520 | 4160
M | 9 " x 6" Lintels reinforced with 04 nos 10mm FFL | 53 | Ft. | 890 | 47170
N | 4.5 " x 6" Lintels reinforced with 02 nos 10mm in 2nd F | 12 | Ft. | 546 | 6552
P | 9 " x 6" Lintels reinforced with 04 nos 10mm in 2nd F | 60 | Ft. | 930 | 55800
| Total C/F |  |  |  | 995108.7
| Total B/F |  |  |  | 995108.7
REINFORCEMENT
High yield deformed steel bar reinforcement yield stress not less than 460N/mm2
column sectional areas and beams and slabs from Ground floor to First Floor Level
A | Columns up to first floor slab level | 636 | Kg | 210 | 133560
B | Beams in first floor level | 1656 | Kg | 210 | 347760
C | Slab in first floor level | 2310 | Kg | 210 | 485100
D | stair cases in ground to first floor | 348 | Kg | 210 | 73080
column sectional areas and beams and slabs from First floor to 2nd Floor Level and roof level
E | Columns up to 2nd floor slab level | 424 | Kg | 220 | 93280
F | Beams in 2nd floor level | 2275 | Kg | 220 | 500500
G | Slab in 2nd floor level | 1320 | Kg | 220 | 290400
H | Columns up to roof level | 336 | Kg | 220 | 73920
J | stair cases in first floor to 2nd floor | 300 | Kg | 220 | 66000
FORMWORK
Formwork to give 'as struck' finish
column sectional areas and beams and slabs from Ground floor to First Floor Level
K | Columns up to first floor slab level | 6.3 | Sqr. | 15120 | 95256
L | Beams in first floor level | 4.5 | Sqr. | 16632 | 74844
M | Slab in first floor level | 5.4 | Sqr. | 15876 | 85730.4
N | Stair cases from ground floor to first floor | 1.6 | Sqr. | 16600 | 26560
| Total C/F |  |  |  | 3341099.1
| Total B/F |  |  |  | 3341099.1
column sectional areas and beams and slabs from First floor to 2nd Floor Level and roof level
A | Columns up to 2nd floor slab level | 3.8 | Sqr. | 15725 | 59755
B | Beams in 2nd floor level | 4.2 | Sqr. | 17300 | 72660
C | Slabs in 2nd floor level | 8.4 | Sqr. | 16500 | 138600
D | Columns up to roof level | 3.9 | Sqr. | 16354 | 63780.6
E | Stair cases from first floor to 2nd Floor | 1.6 | Sqr. | 17264 | 27622.4
| Total Carried to Collection |  |  |  | 3703517.1
B- MASONRY WORK
Ground floor
F | 4.5" thick brick work 1:5 in cement sand mortar- | 0 | Sqr. | 21466.2 | Nil
G | 9" thick brick work 1:5 in cement sand mortar | 1 | Sqr. | 38090.4 | 38090.4
First floor
H | 4.5" thick brick work 1:5 in cement sand mortar | 1.3 | Sqr. | 22488.4 | 29234.92
J | 9" thick brick work 1:5 in cement sand mortar | 12.7 | Sqr. | 38897.4 | 493996.98
Second floor
K | 4.5" thick brick work 1:5 in cement sand mortar | 3.3 | Sqr. | 23564.4 | 77762.52
L | 9" thick brick work 1:5 in cement sand mortar | 17.3 | Sqr. | 39973.4 | 691539.82
| Total Carried to Collection |  |  |  | 1330624.64
C- ASPHALT WORK
Brush applied "Tharoseal" waterproofing system, applied strictly in accordance with manufacturer's printed instructions including all necessary additional strips at angles and duct outlet openings, bath room walls and floor intersections etc., complete pointed with sealant all as specified (contractor to allow for 10 year guarantee and minimum 24 hour flood test)all as approved by client,
A | Bathroom floor and Walls in First Floor | 1.9 | Sqr. | 16500 | 31350
B | Bathroom floor and Walls in 2nd Floor | 1.9 | Sqr. | 16500 | 31350
C | Roof Water tank and Gutter slab | 3.2 | Sqr. | 16500 | 52800
| Total Carried to Collection |  |  |  | 115500
D- ROOFER AND ROOF PLUMBING
D | 0.47mm Zn/Al roof with lunumidella exposed rafter ceiling rate shall including rafters 2X5 , 3 x 8 purling , 3 x 4 wall plates 1 x 2 reapers , 5mm double side foil , polysheet and painting roof with one coat of wood preservative and one coat of wood sheen pine and one coat of mat varnish. | 9.7 | Sqr. | 78010 | 756697
E | Supply and fix 0.47mm Zn/Al valance board | 84 | Ft. | 426 | 35784
F | Supply and fix 0.47mm Zn/Al gutter | 22 | Ft. | 396 | 8712
G | Supply and fix 0.47mm Zn/Al bardge flashing and wall flashing | 50 | Ft. | 396 | 19800
H | Supply & lay 0.47mm Zn/Al rain water down pipes | 64 | Ft. | 396 | 25344
| Total Carried to Collection |  |  |  | 846337
E- METAL WORK
STAIRCASE HANDRAIL
A | 3'-0" high hand rails consisting of 2" diameter Epoxy painted MS top rail, 1.5" diameter MS verticals and 0.5" diameter MS internal horizontal rails including necessary fixing methods as per detail drawings. | 45 | Ft. | 3062.5 | 137812.5
GRILL WORK
B | Fabricate and fixing Grill Work Type GW1 size 38'-7" x 9'-0" of Epoxy painted 4"x 2" Box Iron frame work with 2"x 2" box iron verticals fix to frame. | 1 | No. | 62499.6 | 62499.6
C | Fabricate and fixing Grill Work Type GW1 size 38'-7" x 13'-9" of Epoxy painted 4"x 2" Box Iron frame work with 2"x 2" box iron verticals fix to frame. | 1 | No. | 95485.5 | 95485.5
| Total Carried to Collection |  |  |  | 295797.6
F- DOORS AND WINDOWS
GROUND, FIRST FLOOR AND SECOND FLOOR
TIMBER DOORS
D | Door type D2, size 3'-6" X 8'-0" high, Solid timber paneled Single Sash Door . As per detail drawing. Rate shall include for locks and all necessary ironmongery, and all as per detail drawings and specifications. | 7 | Nos. | 50400 | 352800
E | Door type D3, size 2'-9" X 8'-0" high, Solid timber paneled Single Sash Door . As per detail drawing. Rate shall include for locks and all necessary ironmongery, and all as per detail drawings and specifications. | 2 | Nos. | 39600 | 79200
| Total C/F |  |  |  | 432000
| Total B/F |  |  |  | 432000
ALUMINIUM GLAZED DOORS AND WINDOWS
A | Powder coated approved colour aluminum framed doors, windows units consisting of aluminium frames, transoms, mullians, aluminum framed glazed panels, aluminum louvered panels including necessary hardware such as hinges, floor hinges, fasteners, stays, bolts, locks, handles and the like all as detail drawing, iron mongery schedule and specification.
B | Single sash sliding Door type SD4, size 9'-10"x 8'-0" high overall aluminum framed glazed door and fixed glass window as per detail drawing. | 1 | Nos. | 149416 | 149416
C | Single sash sliding Door type SD5, size 10'-4"x 8'-0" high overall aluminum framed glazed door and fixed glass window as per detail drawing. | 1 | Nos. | 157016 | 157016
D | Two sash sliding Window type SW3, size 7'-6"x 8'-0" high overall aluminum framed glazed window as per detail drawing. | 1 | Nos. | 114000 | 114000
E | Two sash sliding Window type SW4, size 7'-0"x 8'-0" high overall aluminum framed glazed window as per detail drawing. | 3 | Nos. | 106400 | 319200
F | Two sash sliding Window type SW5, size 5'-0"x 4'-9" high overall aluminum framed glazed window as per detail drawing. | 2 | Nos. | 45125 | 90250
G | Two sash sliding Window type SW6, size 6'-0"x 5'-0" high overall aluminum framed glazed window as per detail drawing. | 1 | Nos. | 57000 | 57000
H | Fixed Glass Window type FG1, size 4'-0"x 5'-0" high overall aluminum framed glazed window as per detail drawing. | 2 | Nos. | 34000 | 68000
J | Fixed Glass Window type F3, size 2'-6"x 3'-0" high overall aluminum framed glazed window as per detail drawing. | 2 | Nos. | 12750 | 25500
| Total C/F |  |  |  | 1412382
| Total B/F |  |  |  | 1412382
ROLLER DOOR
A | Roller door type RD1, size 35'-0' x 8'-0" high overall roller door with powder coated aluminum box cover as per detail drawing. | 1 | Nos. | 392000 | 392000
| Total Carried to Collection |  |  |  | 1804382
G- FINISHES
FLOOR FINISHES
Wall tiles
Lay 18''x12" wall tiles with tile adhesive finish with grouting in toilet walls. PC Rate per tile sqft Rs. 300
B | In Ground floor | 0 | Sqr | 55952 | Nil
C | In first floor | 1.6 | Sqr | 56490 | 90384
D | In 2nd floor | 1.6 | Sqr | 56490 | 90384
Floor tiling
To approved design and colour and including 20mm thick cement and sand (1:3) screed bedding level
Lay 18"x18" floor tiles with tile adhesive finish with grouting. Rate per tile sqft Rs. 260.00
E | in Ground floor | 0.3 | Sqr | 51110 | 15333
F | 4" height skirting | 0 | Ft | 168.66 | Nil
G | 10" Wide Steps | 53 | Ft | 424.21 | 22483.13
H | 6" Height Riser | 69 | Ft | 255.55 | 17632.95
| Total C/F |  |  |  | 236217.08
| Total B/F |  |  |  | 236217.08
A | In first floor | 6.4 | Sqr | 51621.1 | 330375.04
B | 4" height skirting | 180 | Ft | 170.35 | 30663
C | 10" Wide Steps | 53 | Ft | 428.46 | 22708.38
D | 6" Height Riser | 69 | Ft | 258.11 | 17809.59
E | Pantry worktop | 0.6 | Sqr | 51621.1 | 30972.66
F | In 2nd floor | 6.2 | Sqr | 52137.31 | 323251.32
G | 4" height skirting | 192 | Ft | 172.05 | 33033.6
H | 10" Wide Steps | 53 | Ft | 432.74 | 22935.22
J | 6" Height Riser | 69 | Ft | 260.69 | 17987.61
K | Pantry worktop | 0.6 | Sqr | 52137.31 | 31282.39
Internal plaster
L | 16mm thick 1:5 cement sand plastering Ground floor | 6.6 | Sqr | 8166.84 | 53901.14
M | 16 mm thick 1:5 cement sand plastering-First floor | 19.8 | Sqr | 8403.56 | 166390.49
N | 16mm thick 1:5 cement sand plastering -2nd floor | 31.8 | Sqr | 8640.28 | 274760.9
Beam and column plaster
P | 16mm thick 1:5 cement sand plastering - Ground floor | 5 | Sqr | 10060.6 | 50303
Q | 16mm thick 1:5ement sand plastering - First floor | 1.7 | Sqr | 10415.68 | 17706.66
R | 16mm thick 1:5 cement sand plastering-2nd floor | 1 | Sqr | 10652.4 | 10652.4
Revil plaster
S | 16mm thick 1:5 cement sand plastering finishing GF | 40 | Ft | 61.88 | 2475.2
T | 16mm thick 1:5 cement sand plastering - F F | 196 | Ft | 65.31 | 12800.76
U | 16mm thick 1:5 cement sand plastering 2nd F | 311 | Ft | 68.75 | 21381.25
| Total C/F |  |  |  | 1707607.69
| Total B/F |  |  |  | 1707607.69
Soffit Plastering
A | 16mm thick 1:5 cement sand plastering finishing semi rough under faces of slabs- G F floor | 7.1 | Sqr | 7989.3 | 56724.03
B | 16mm thick 1:5 cement sand soffit plastering finishing semi rough on surfaces of slab -First floor | 6.9 | Sqr | 8403.56 | 57984.56
External plaster
C | 16mm thick 1:5 cement sand plastering finishing semi rough on external faces of walls - Ground floor | 4 | M2 | 7279.14 | 29116.56
D | 16 mm thick 1:5 cement sand plastering finishing semi rough on external faces of walls -First floor | 4.2 | M2 | 7456.68 | 31318.06
E | 16mm thick 1:5 cement sand plastering finishing semi rough on external faces of walls -2nd floor | 5.9 | M2 | 7693.4 | 45391.06
External Revil plaster
F | 16mm thick 1:5 cement sand plastering finishing semi rough on Revils - ground floor | 40 | Ft. | 70.43 | 2817.2
G | 16mm thick 1:5 cement sand plastering finishing semi rough on Revils - F F floor | 79 | Ft. | 73.78 | 5828.62
H | 16mm thick 1:5 cement sand plastering finishing semi rough on Revils - 2nd floor | 118 | Ft. | 75.46 | 8904.28
Plinth Plaster
J | 20mm Thick plinth plaster in cement and sand 1:1 finished smooth with neat cement | 2.1 | Sqr | 15268.44 | 32063.72
| Total C/F |  |  |  | 1977755.78
| Total B/F |  |  |  | 1977755.78
PAINTING AND DECORATING
Two coat of emulsion paint & one coat acrylic filler & suitable under coat as per manufacture's instructions to internal plastered walls. Paint shall be used by CIC and wall piller by Asian Paints
Internal painting
A | Ground Floor | 11.6 | Sqr | 6348.4 | 73641.44
B | First Floor | 21.5 | Sqr | 6563.6 | 141117.4
C | 2ndFloor | 32.8 | Sqr | 6778.8 | 222344.64
Two coat of emulsion paint & one coat acrylic filler & suitable under coat as per manufacture's instructions to internal plastered soffits.
D | Ground floor | 7.1 | Sqr | 6617.4 | 46983.54
E | First floor | 6.9 | Sqr | 6940.2 | 47887.38
F | Staircase Ground to 2nd Floor | 1.2 | Sqr | 7155.4 | 8586.48
Two coat of emulsion paint, one coat acrylic filler & two coat of skim coat & suitable under coat as per manufacture's instructions to internal plastered revils.
G | Ground Floor | 40 | Ft. | 50.3 | 2012
H | First Floor | 196 | Ft. | 53.35 | 10456.6
J | 2ndFloor | 311 | Ft. | 54.88 | 17067.68
External painting
Two coat of weather shield paint & one coat of primer under coat paint, as per manufacture's instructions to external plastered walls.
K | Ground floor | 4 | Sqr | 7532 | 30128
L | First Floor | 4.2 | Sqr | 7757.96 | 32583.43
| Total C/F |  |  |  | 2610564.37
| Total B/F |  |  |  | 2610564.37
A | 2nd Floor | 5.9 | Sqr | 7983.92 | 47105.13
Two coat of weather shield paint, one coat of primer & two coat of skim under coat paint, as per manufacture's instructions to external plastered revils.
B | Ground floor | 40 | Ft. | 39.63 | 1585.2
C | First Floor | 79 | Ft. | 42.07 | 3323.53
D | 2nd Floor | 118 | Ft. | 43.29 | 5108.22
| Total Carried to Collection |  |  |  | 2667686.45
H - ELECTRICAL WORK
Lamp point with Switch
Wiring of all lamp points one way or two way including PVC conduit, with 2x1mm2 Cu/PVC/PVC wires and supply and fixing of switches all as show in approved drawings and all materials approved by client.
E | Light Point including external wall light | 28 | nr | 2279 | 63812
F | Two way light point | 6 | nr | 2915 | 17490
Bell push point with Switch
G | Wiring of bell push point including PVC conduit, with 2x1mm2 Cu/PVC/PVC wires and supply and fixing of Bell push switched all as show in approved drawings | 2 | nr | 3600 | 7200
Fixing of light fittings
fixing of any type of Pendent lamp, Wall lamp, Spot light or any other light fittings complete with screws, anchor bolts, role plugs all materials approved by client. ( cost for fitting Rs: 2500.00)
H | Pendent light | 16 | nr | 3225 | 51600
J | Wall lamp | 6 | nr | 3225 | 19350
K | External Wall lamp | 2 | nr | 3225 | 6450
| Total C/F |  |  |  | 165902
| Total B/F |  |  |  | 165902
Socket outlet(5A/5A W/P/multi Socket)with Wiring
A | Wiring of 5A,5A W/P , Multi Socket outlet including PVC conduit, 2x1.5mm2 Cu/PVC/PVC with 2.5mm2 earth wires and supply and fixing of Socket outlet(5A/5A W/P/multi Socket all as show in approved drawings and all materials approved by client. | 0 | nr | 2750 | Nil
Socket outlet(13A/13A W/P)with Wiring
B | Wiring of 13A/13A W/P Socket outlet including PVC conduit, 2x2.5mm2 Cu/PVC/PVC with 2.5mm2 earth wires and supply and fixing of Socket outlet(13A/13A W/P) all as show in approved drawings and all materials approved by client. | 24 | nr | 4187 | 100488
Socket outlet(15A/15A W/P)with Wiring
C | Wiring of 15A/15A W/P Socket outlet including PVC conduit, 2x2.5mm2 Cu/PVC/PVC with 2.5mm2 earth wires and supply and fixing of Socket outlet(15A/15A W/P) all as show in approved drawings and all materials approved by client. | 4 | nr | 5280 | 21120
External garden light
D | Wiring of External garden light in two way, including PVC conduit, with 2x1mm2 Cu/PVC/PVC wires and supply and fixing of switches (fixing of switches in house ,location approved by client) including fixing of any type of garden light fitting (cost of the fitting Rs: 5000.00), all as show in approved drawings or instruct by client and all materials approved by client. | 2 | nr | 8670 | 17340
Telephone/Data/Pro TV Socket outlet with Wiring
E | Wiring of Telephone/Data/Pro TV Socket outlet including PVC conduit, 8x0.50mm2 Cu/PVC/PVC 4pair (cat5)cable and supply and fixing of Telephone/Data/Pro TV Socket outlet all as show in approved drawings and all materials approved by client. | 2 | nr | 4800 | 9600
TV Socket outlet with Wiring
F | Wiring of TV Socket outlet including PVC conduit, RG6 cable and supply and fixing of TV Socket outlet all as show in approved drawings and all materials approved by client. | 4 | nr | 4300 | 17200
| Total C/F |  |  |  | 331650
| Total B/F |  |  |  | 331650
CCTV system Wiring
G | Wiring of CCTV system including PVC conduit,RG6+Hat.twin cable all as show in approved drawings and all materials approved by client. | 2 | nr | 2750 | 5500
Main Distribution Unit complete with wiring and testing
H | Supply and Fixing of Main DB ,including RCCB,MCB,Isolator all as approved by Client ,complete with wiring and testing
1 flush type panel 400x700X125mm
13 MCB SP 10A brand Hanger
03 MCB SP 16A
01 MCB TP 40A
01 MCB 4P 20A
01 MCB 4P 63A
04 RCCB DP 40A 30mA
| Internal wiring and other accessories | 2 | nr | 72500 | 145000
Incoming main Cable from CEB meter to main DB
J | Supply install & connected 4x16mm2 Cable+ 6mm2 earth cable from Incoming main Cable from CEB meter to main DB including PVC conduit and all materials approved by client. | 90 | Ft. | 950 | 85500
Meter box enclosure for CEB meter
K | Supply and fixing of powder coated metering box wall mounted panel 400x500X200mm flush type | 2 | nr | 8200 | 16400
Earth Electrode
J | Supply & installation of Earth Electrode (16mm copper bounded)as approved by the Client including 6mm earth wires | 2 | nr | 7200 | 14400
CEB Power Connection
K | Allow Provisional Sum to get the CEB Power connection | 1 | Item | 40000 | 40000
| Total Carried to Collection |  |  |  | 638450
J- PLUMBING WORK
Pipe Laying ( For Water Supply)
Supply and install high pressure PVC water supply pipe work with fittings (below ground or above ground) complete with excavation if required or connections, supports and accessories; all in accordance with the drawings and approved by client (rate to include for complete pressure testing)
A | Using 20mm(1/2") (Type1000) pipes For Water Distribution Inside of the Bath Rooms & others | 60 | Ft | 120.7 | 7242
B | Using 32mm(1") (Type1000) pipes For Water Distribution Inside of the Bath Rooms & others | 30 | Ft | 152.06 | 4561.8
Pipe laying (for waste water line)
Supply and PVC waste water line (T - 600 )pipe work with fittings (below ground or above ground) complete with excavation if required or connections, supports and accessories; all in accordance with the drawings and approved by client (rate to include for complete pressure testing)
C | Using 40mm(1 1/4")(Type600) pipes For Waste water line from wash basin to floor gully | 18 | Ft | 148.44 | 2671.92
D | Using 63mm(2")(Type600) pipes For Waste Water line from floor gully to waste water gully, kitchen sink to kitchen gullies. | 32 | Ft | 359.38 | 11500.16
E | Using 75mm(2 1/2")(Type600) pipes For Waste water line among kitchen gullies. | 90 | Ft | 515.63 | 46406.7
Pipe Laying (For sewerage & Waste Water Lines)
F | Using 110mm (4")(Type 600) Pipes For Sewerage lines & waste water lines between water closets & man holes, waste water gullies(All pip | 60 | Ft | 609.38 | 36562.8
| Total C/F |  |  |  | 108945.38
| Total B/F |  |  |  | 108945.38
Gullies
A | Sealed gully , (300x300x 300 to 450 deep ) as specified and detailed on drawing (for Waste Water Gullies) (as approved by client) including cover slab | 2 | Nos | 4500 | 9000
B | Sealed gully , (300x300x 300 to 450 deep ) as specified and detailed on drawing (for Rain Water gullies) (as approved by client) including cover slab | 2 | Nos | 4500 | 9000
C | Sealed gully , (300x300x 300 to 450 deep ) as specified and detailed on drawing (for Kitchen Waste Water gullies) (as approved by client) including cover slab. | 1 | Nos | 4500 | 4500
Man Holes
D | Internal size 375mm x 375mm average 450 mm deep to invert, including all associated work all as specified and shown on drawings (as approved by client) including cover slab. | 2 | Nos | 6500 | 13000
Water Tank
E | Supply and Fixing the Plastic Water tank 1500 ltrs including all fitting & accessories | 2 | Nos | 15500 | 31000
Supply and Fixing of Bath Room Fittings / Accessories
F | Basin Mixer tap | 2 | Nos | 4950 | 9900
G | telephone Shower pipe | 2 | Nos | 4500 | 9000
H | Sink Mixer tap | 2 | Nos | 4200 | 8400
J | Bidet Spray | 2 | Nos | 1750 | 3500
K | 6 pcs. Essentials Accessory Set | 2 | Nos | 4500 | 9000
L | Wash Basin | 2 | Nos | 10150 | 20300
M | Water Closet | 2 | Nos | 17850 | 35700
N | 6"x6" Floor Gullies | 2 | Nos | 2450 | 4900
P | Bath Room Mirror | 2 | Nos | 2500 | 5000
| Total C/F |  |  |  | 281145.38
| Total B/F |  |  |  | 281145.38
Supply and Fixing of Bath Room Fittings / Accessories Contd..
A | Bottle Traps | 4 | Nos | 4250 | 17000
B | gate valve pegler 1" dia | 4 | Nos | 2500 | 10000
Waste Water, Kitchen waste and Rain water Pit
C | Supply and placing of precast soakage pit with precast cover slab , Excavation 5ft Dia X 7ft Height for Waste Water Pit with back filling with 3/4" thick metal layer for filter material . As per the approved Location by client. Including laying & connecting the Pipe work inlet & outlet. placing of cover slab and making slab opening in 450X450 size brick wall up to finish floor level with smooth plaster for covering around the opening and placing concrete cover slab for top cover all as approved by Client | 3 | Nos | 53130 | 159390
Septic Tank with Soakage Pit
D | Supply and placing of precast Precast Septic Tank 8'X3' dia and soakage pit with cover slab 3' dia Excavation 9'x4'x5'for Septic Tank & 4ft Dia X 7ft Height for Soakage pit. Including 6" thick sand Bed for Septic Tank. Placing of Precast Septic Tank back filling with approved available soil. and soakage pit back filling with 3/4" thick metal layer for filter material . As per the approved Location by Client. Including , laying & connecting the Pipe work inlet & outlets. placing of cover slab and making slab opening in 450X450 size brick wall up to finish floor level with smooth plaster for covering around the opening and placing concrete cover slab for top cover all as approved by Client | 2 | Nos | 75700 | 151400
Water Supply connection from NWS&DB
| Allow Provisional Amount to Water Supply connection from NWS&DB | 2 | Item | 24000 | 48000
| Total Carried to Collection |  |  |  | 666935.38
COLLECTION - BILL NO. 03
BILL NO. 03- SUPERSTRUCTURE
| A- CONCRETE WORK |  |  |  | 3703517.1
| B- MASONRY WORK |  |  |  | 1330624.64
| C- ASPHALT WORK |  |  |  | 115500
| D- ROOFER AND ROOF PLUMBING |  |  |  | 846337
| E- METAL WORK |  |  |  | 295797.6
| F- DOORS AND WINDOWS |  |  |  | 1804382
| G- FINISHES |  |  |  | 2667686.45
| H - ELECTRICAL WORK |  |  |  | 638450
| J- PLUMBING WORK |  |  |  | 666935.38
| Total Bill No. 03- Carried to Summary |  |  |  | 12069230.17
SUMMARY
BILL NO. 01- PRELIMINARIES & DEMOLITION WORK
| A- PRELIMINARIES |  | 85000
| B- DEMOLITION WORK |  | 540000
| Sub Total Bill No. 01- |  | 625000 |  | 625000
BILL NO. 02- SUBSTRUCTURE
| C- EXCAVATION AND EARTH WORK |  | 175858
| D- CONCRETE WORK |  | 775043.5
| E- MASONRY WORK |  | 332156
| F- ASPHALT WORK |  | 25170.6
| Sub Total Bill No. 02- |  | 1308228.1 |  | 1308228.1
BILL NO. 03- SUPERSTRUCTURE
| A- CONCRETE WORK |  | 3703517.1
| B- MASONRY WORK |  | 1330624.64
| C- ASPHALT WORK |  | 115500
| D- ROOFER AND ROOF PLUMBING |  | 846337
| E- METAL WORK |  | 295797.6
| F- DOORS AND WINDOWS |  | 1804382
| G- FINISHES |  | 2667686.45
| H - ELECTRICAL WORK |  | 638450
| J- PLUMBING WORK |  | 666935.38
| Sub Total Bill No. 03- |  | 12069230.17 |  | 12069230.17
| GRAND TOTAL |  |  |  | 14002458.27 | 10501843.7
Amount in Wards: Rupees Fourteen Million Two Thousand and Four Hundred and Fifty Eight and Cents Twenty Seven only.
Certified by:
…………………………
A.D. Amith Priyantha,
BSc(Hons) Quantity Surveying &
Construction Management.
No.3/81, Gangarama Road, Wewala,
Piliyandala. Tel: 0777 23945
Date: 02.09.2019

## Total Measurement (hidden)
double wall with every thing , external finishes same as lot 9 | [5 empty] | 13324449.39 | [7 empty] | Client Supply Material
Item | Description | Qty | Unit | Rate | Amount |  | T | T | L | W | H | Qty | Final Qty | Floor and Wall tile |  | Floor Carpert |  | Light fittings |  | Sanitary fittings
A | EXCAVATION AND EARTH WORK
2.83
A1 | Excavation for columns/ Staircase foundation | 8 | Cube | 3950 | 31600 | Column |  | 20 | 3.5 | 3.5 | 3 | 735
[6 empty] | Staircase |  | 1 | 15 | 2 | 2 | 60
[12 empty] | 795 | 8
0
A2 | Excavation for wall/ Boundry Wall foundation | 7.8 | Cube | 3660 | 28548 | C/C Wall Fdn |  | 1 | 137 | 1.5 | 2 | 411
[6 empty] | B.Wall Fdn |  | 1 | 41 | 1.5 | 1.5 | 92.25
[6 empty] | Ret. Wall |  | 1 | 44 | 2.5 | 2.5 | 275
[12 empty] | 778.25 | 7.8
A3 | Well compacted, approved imported earth filling, | 20.3 | Cube | 5700 | 115710 |  |  | 1 | 35 | 16 | 1 | 560
[8 empty] | 1 | 35 | 21 | 2 | 1470
| TOTAL FOR EXCAVATION |  |  |  | 175858 | [6 empty] | 2030 | 20.3
B | CONCRETE WORKS
Foundation up to DPC Level
Grade 15 Concrete in the following.
B1 | 2" thk. concrete under columns/Staircase base | 2.8 | Sqr. | 6640 | 18592 | Column |  | 20 | 3.5 | 3.5 |  | 245
[6 empty] | Staircase |  | 1 | 15 | 2 |  | 30
[12 empty] | 275 | 2.8
B2 | 2" thk. concrete under rubble work | 2.3 | Sqr. | 6640 | 15272 | C/C Wall Fdn |  | 1 | 56 | 1.5 |  | 84
[6 empty] | B.Wall Fdn |  | 1 | 23 | 1.5 |  | 34.5
[6 empty] | Ret. Wall |  | 1 | 41 | 2.5 |  | 102.5
[12 empty] | 221 | 2.3
B3 | 3" thk. Concrete floor slab | 13 | Sqr. | 9910 | 128830 |  |  | 1 | 35 | 16 |  | 560
[8 empty] | 1 | 35 | 21 |  | 735
| Grade 25 R.C. Concrete in the following. | [10 empty] | 1295 | 13
B4 | column sectional areas and beams and slabs in GF
B4-01 | columns/Staircase base concreting | 2.4 | Cube | 40480 | 97152 | Column |  | 20 | 3.5 | 3.5 | 0.75 | 183.75
[6 empty] | Ret. Wall Column |  | 6 | 2.5 | 2.5 | 0.75 | 28.13
[6 empty] | Staircase |  | 1 | 15 | 2 | 0.75 | 22.5
[12 empty] | 234.38 | 2.4
B4-02 | column/Staircase shaft concreting up to plinth beam level | 0.8 | Cube | 40480 | 32384 | Column |  | 20 | 0.75 | 0.75 | 3.5 | 39.38
[6 empty] | Ret. Wall Column |  | 6 | 0.75 | 0.75 | 5 | 16.88
[6 empty] | Staircase |  | 1 | 15 | 0.5 | 2.5 | 18.75
[12 empty] | 75.01 | 0.8
B4-04 | 12" x 4" plinth beams | 1.1 | Cube | 40480 | 44528 | C/C Wall Fdn |  | 1 | 75 | 1 | 0.33 | 24.75
[6 empty] | C/C Wall Fdn |  | 1 | 150 | 1 | 0.33 | 49.5
[6 empty] | B.Wall Fdn |  | 1 | 46 | 1 | 0.33 | 15.18
[6 empty] | Ret. Wall |  | 1 | 41 | 1 | 0.33 | 13.53
[12 empty] | 102.96 | 1.1
B5 | column sectional areas and beams and slabs in FFL
B5-01 | columns up to first floor slab level | 1.2 | Cube | 41998 | 50397.6 | Column |  | 20 | 0.75 | 0.75 | 10.5 | 118.13 | 1.2
B5-02 | Slab beams at first floor slab level | 1.4 | Cube | 41998 | 58797.2 | Rent Beam |  | 1 | 192 | 0.75 | 0.58 | 83.52
[6 empty] | Beam |  | 1 | 109 | 0.75 | 0.58 | 47.42
[12 empty] | 130.94 | 1.4
B5-03 | first floor slab | 7.7 | Cube | 41998 | 323384.6 | Rent Slab |  | 1 | 38 | 20 | 0.42 | 319.2
[6 empty] | Slab |  | 1 | 39 | 27 | 0.42 | 442.26
[12 empty] | 761.46 | 7.7
B5-04 | stair case concrete | 0.6 | Cube | 41998 | 25198.8 | Rent Slab | 0.5 | 18 | 3.5 | 0.83 | 0.5 | 13.07
[6 empty] | waSTE |  | 1 | 13 | 3.5 | 0.33 | 15.02
[6 empty] | Slab | 0.5 | 19 | 0.83 | 0.5 | 3.94 | 15.53
[6 empty] | waSTE |  | 1 | 13 | 3.5 | 0.33 | 15.02
[12 empty] | 58.64 | 0.6
B6 | column sectional areas and beams and slabs in 2nd FL
B6-01 | columns up to 2nd floor slab level | 0.8 | Cube | 43010 | 34408 | Column |  | 12 | 0.75 | 0.75 | 10.5 | 70.88 | 0.8
B6-02 | Slab beams at 2nd floor slab level | 3.25 | Cube | 43010 | 139782.5 | Rent Beam |  | 1 | 215 | 0.75 | 0.58 | 93.53
[6 empty] | Beam |  | 0 | 109 | 0.75 | 0.58 | 0
[12 empty] | 93.53 | 1
B6-03 | 2nd floor slab | 4.4 | Cube | 43010 | 189244 | Rent Slab |  | 1 | 38 | 20 | 0.42 | 319.2
[6 empty] | Rent Slab Gutter |  | 1 | 20 | 4 | 0.75 | 60
[6 empty] | Slab |  | 0 | 39 | 27 | 0.42 | 0
[6 empty] | W.tank slab |  | 1 | 16 | 10 | 0.33 | 52.8
[12 empty] | 432 | 4.4
B6-04 | Columns up to roof level | 0.8 | Cube | 43010 | 34408 | Rent Column | 12 | 0.75 | 0.75 | 10.66 | 71.96 | 0.8
W.tank slab
B6-05 | stair case concrete | 0.6 | Cube | 43010 | 25806 | Rent Slab | 0.5 | 18 | 3.5 | 0.83 | 0.5 | 13.07
[6 empty] | waSTE |  | 1 | 13 | 3.5 | 0.33 | 15.02
[6 empty] | Slab | 0.5 | 19 | 0.83 | 0.5 | 3.94 | 15.53
[6 empty] | waSTE |  | 1 | 13 | 3.5 | 0.33 | 15.02
[12 empty] | 58.64 | 0.6
B7 | lintels and window cills
Ground floor
iii | 4.5 " x 6" Lintels reinforced with 02 nos 10mm | 0 | Ft. | 1320 | 0
ii | 9 " x 6" Lintels reinforced with 04 nos 10mm | 0 | Ft. | 2290 | 0
first floor
vi | 4.5 " x 6" Lintels reinforced with 02 nos 10mm | 8 | Ft. | 520 | 4160
vii | 9 " x 6" Lintels reinforced with 04 nos 10mm | 53 | Ft. | 890 | 47170
B8 | Second floor
vi | 4.5 " x 6" Lintels reinforced with 02 nos 10mm | 12 | Ft. | 546 | 6552
vii | 9 " x 6" Lintels reinforced with 04 nos 10mm | 60 | Ft. | 930 | 55800
| TOTAL FOR CONCRETE WORK |  |  |  | 1331866.7
C | REINFORCEMENT
c-01 | columns/Staircase base | 984 | Kg | 200 | 196800
c-02 | Columns up to plinth beam level | 400 | Kg | 200 | 80000
c-03 | Plinth beams | 297 | Kg | 200 | 59400
c-04 | Columns up to first floor slab level | 636 | Kg | 210 | 133560
c-05 | Beams in first floor level | 1656 | Kg | 210 | 347760
| Slab in first floor level | 2310 | Kg | 210 | 485100
| stair cases in ground to first floor | 348 | Kg | 210 | 73080
c-06 | Columns up to 2nd floor slab level | 424 | Kg | 220 | 93280
| Beams in 2nd floor level | 2275 | Kg | 220 | 500500
c-07 | Slab in 2nd floor level | 1320 | Kg | 220 | 290400
c-08 | Columns up to roof level | 336 | Kg | 220 | 73920
c-09 | stair cases in first floor to 2nd floor | 300 | Kg | 220 | 66000
| TOTAL FOR REINFORCEMENT WORK |  |  |  | 2399800
D | FORM WORKS
d-01 | Column base and column shaft up to plinth level | 5.8 | Sqr. | 14795 | 85811 | Column | 4 | 20 | 3.5 |  | 0.75 | 210
[6 empty] | Ret. Wall Column | 4 | 6 | 2.5 |  | 0.75 | 45
[6 empty] | Staircase | 2 | 1 | 0 | 2 | 0.75 | 0
[6 empty] | Column | 4 | 20 | 0.75 |  | 3.5 | 210
[6 empty] | Ret. Wall Column | 4 | 6 | 0.75 |  | 5 | 90
[6 empty] | Staircase | 2.5 | 1 | 3.5 |  | 2.5 | 21.88
[12 empty] | 576.88 | 5.8
d-02 | Plinth beams | 1.1 | Sqr. | 14795 | 16274.5 | C/C Wall Fdn |  | 1 | 75 | 1 | 0.33 | 24.75
[6 empty] | C/C Wall Fdn |  | 1 | 150 | 1 | 0.33 | 49.5
[6 empty] | B.Wall Fdn |  | 1 | 46 | 1 | 0.33 | 15.18
[6 empty] | Ret. Wall |  | 1 | 41 | 1 | 0.33 | 13.53
[12 empty] | 102.96 | 1.1
d-03 | Columns up to first floor slab level | 6.3 | Sqr. | 15120 | 95256 | Column | 4 | 20 | 0.75 |  | 10.5 | 630 | 6.3
| Beams in first floor level | 4.5 | Sqr. | 16632 | 74844 | Rent Beam |  | 2 | 192 |  | 0.58 | 222.72
[8 empty] | 1 | 192 | 0.75 |  | 144
[6 empty] | Beam |  | 1 | 109 | 0.75 |  | 81.75
[8 empty] | 2 | 109 |  | 0.58 | 126.44
[12 empty] | 448.47 | 4.5
d-04 | Slab in first floor level | 5.4 | Sqr. | 15876 | 85730.4 | Rent Slab |  | 1 | 38 | 20 | 0.42 | 319.2
[6 empty] | Less col |  | -1 | 192 | 0.75 |  | -144
[6 empty] | Slab |  | 1 | 39 | 27 | 0.42 | 442.26
[6 empty] | Less col |  | -1 | 109 | 0.75 |  | -81.75
[12 empty] | 535.71 | 5.4
| Stair cases from ground floor to first floor | 1.6 | Sqr. | 16600 | 26560 | Rent Slab |  | 18 | 3.5 |  | 0.5 | 31.5
[6 empty] | waSTE side |  | 2 | 13 |  | 0.33 | 8.58
[6 empty] | waSTE |  | 1 | 13 | 3.5 |  | 45.5
[6 empty] | Slab | 0.5 | 19 | 0.83 | 0.5 | 3.94 | 15.53
[6 empty] | waSTE side |  | 2 | 13 |  | 0.33 | 8.58
[6 empty] | waSTE |  | 1 | 13 | 3.5 |  | 45.5
[12 empty] | 155.19 | 1.6
d-05 | Columns up to 2nd floor slab level | 3.8 | Sqr. | 15725 | 59755 | Column | 4 | 12 | 0.75 |  | 10.5 | 378 | 3.8
| Beams in 2nd floor level | 4.2 | Sqr. | 17300 | 72660 | Rent Beam |  | 2 | 215 |  | 0.58 | 249.4
[8 empty] | 1 | 215 | 0.75 |  | 161.25
[6 empty] | Beam |  | 0 | 109 | 0.75 | 0.58 | 0
[12 empty] | 410.65 | 4.2
| Slabs in 2nd floor level | 8.4 | Sqr. | 16500 | 138600 | Rent Slab |  | 1 | 38 | 20 |  | 760
[6 empty] | Less beam |  | -1 | 215 | 0.75 |  | -161.25
[6 empty] | Rent Slab Gutter |  | 1 | 20 | 4 |  | 80
[6 empty] | Slab |  | 0 | 39 | 27 |  | 0
[6 empty] | W.tank slab |  | 1 | 16 | 10 |  | 160
[12 empty] | 838.75 | 8.4
d-07 | Columns up to roof level | 3.9 | Sqr. | 16354 | 63780.6 | Rent Column | 4 | 12 | 0.75 |  | 10.66 | 383.76 | 3.9
| Stair cases from first floor to 2nd Floor | 1.6 | Sqr. | 17264 | 27622.4 | Rent Slab |  | 18 | 3.5 |  | 0.5 | 31.5
[6 empty] | waSTE side |  | 2 | 13 |  | 0.33 | 8.58
[6 empty] | waSTE |  | 1 | 13 | 3.5 |  | 45.5
[6 empty] | Slab | 0.5 | 19 | 0.83 | 0.5 | 3.94 | 15.53
[6 empty] | waSTE side |  | 2 | 13 |  | 0.33 | 8.58
[6 empty] | waSTE |  | 1 | 13 | 3.5 |  | 45.5
[12 empty] | 155.19 | 1.6
| TOTAL FOR FORM WORK |  |  |  | 746893.9
E | MASONRY WORK
e-01 | Random rubble masonry work | 11 | Cube | 30196.1 | 332157.1 | C/C Wall Fdn |  | 1 | 137 | 1.58 | 1.5 | 324.69
[8 empty] | 1 | 137 | 1.08 | 1.5 | 221.94
[6 empty] | B.Wall Fdn |  | 1 | 41 | 1.5 | 1.5 | 92.25
[8 empty] | 1 | 41 | 1 | 1 | 41
[6 empty] | Ret. Wall |  | 1 | 44 | 2.5 | 2.5 | 275
[8 empty] | 1 | 44 | 1.25 | 2.5 | 137.5
[12 empty] | 1092.38 | 11
ground floor
e-02 | 4.5" thick brick work 1:5 in cement sand mortar- | 0 | Sqr. | 21466.2 | 0 | [7 empty] | 0
e-03 | 9" thick brick work 1:5 in cement sand mortar | 1 | Sqr. | 38090.4 | 38090.4 | [6 empty] | 97 | 1
first floor
| 4.5" thick brick work 1:5 in cement sand mortar | 1.3 | Sqr. | 22488.4 | 29234.92 | [6 empty] | 125 | 1.3
e-05 | 9" thick brick work 1:5 in cement sand mortar | 12.7 | Sqr. | 38897.4 | 493996.98 | [6 empty] | 1263 | 12.7
e-07
Second floor
e-09 | 4.5" thick brick work 1:5 in cement sand mortar | 3.3 | Sqr. | 23564.4 | 77762.52 | [6 empty] | 325 | 3.3
e-10 | 9" thick brick work 1:5 in cement sand mortar | 17.3 | Sqr. | 39973.4 | 691539.82 | [6 empty] | 1728 | 17.3
| TOTAL FOR MASONARY WORK |  |  |  | 1662781.74
F | ASPHALT WORK
f-01 | Supply and lay 1000 gauge polythene sheet | 13 | Sqr. | 1183.6 | 15386.8
Damp Proof Course
f-02 | Applying 2 coat of DPC tar for Ground Wall Foundation | 2.6 | Sqr. | 3766 | 9791.6 | C/C Wall Fdn |  | 1 | 137 | 1.25 |  | 171.25
[6 empty] | B.Wall Fdn |  | 1 | 41 | 1 |  | 41
[6 empty] | Ret. Wall |  | 1 | 44 | 1 |  | 44
[12 empty] | 256.25 | 2.6
f-05 | Brush applied "Tharoseal" waterproofing system, applied strictly in accordance with manufacturer's printed instructions including all necessary additional strips at angles and duct outlet openings,bath room walls and floor intersections etc., complete pointed with sealant all as specified (contractor to allow for 10 year guarantee and minimum 24 hour flood test)all as approved by client, |  |  |  | 0
| Bathroom floor and Walls in First Floor | 1.9 | Sqr. | 16500 | 31350 | B.Floor |  | 1 | 9 | 4.66 |  | 41.94
[6 empty] | B.Wall |  | 1 | 24.32 |  | 6 | 145.92
[12 empty] | 187.86 | 1.9
| Bathroom floor and Walls in 2nd Floor | 1.9 | Sqr. | 16500 | 31350 | B.Floor |  | 1 | 9 | 4.66 |  | 41.94
[6 empty] | B.Wall |  | 1 | 24.32 |  | 6 | 145.92
[12 empty] | 187.86 | 1.9
| Roof Water tank and Gutter slab | 3.2 | Sqr. | 16500 | 52800 | Rent Slab Gutter |  | 1 | 20 | 4 |  | 80
[6 empty] | Up stand |  | 1 | 48 |  | 0.67 | 32.16
[6 empty] | W.tank slab |  | 1 | 16 | 10 |  | 160
[6 empty] | Up stand |  | 1 | 52 |  | 0.75 | 39
[12 empty] | 311.16 | 3.2
| TOTAL FOR ASPHALT WORK |  |  |  | 140678.4
G | ROOFER AND ROOF PLUMBING
g-01 | 0.47mm Zn/Al roof with lunumidella exposed rafter ceiling rate shall including rafters 2X5 , 3 x 8 purling , 3 x 4 wall plates 1 x 2 reapers , 5mm double side foil , polysheet and painting roof with one coat of wood preservative and one coat of wood sheen pine and one coat of mat varnish. | 9.7 | Sqr. | 78010 | 756697 | Roof |  | 1 | 41 | 23 |  | 943
[8 empty] | 1 | 10.3 | 2.5 |  | 25.75
[8 empty] | 1 | 8.75 | 2.5 |  | 21.88
[8 empty] | -1 | 17 | 2 |  | -34
[12 empty] | 968.75 | 9.7
g-02 | Supply and fix 0.47mm Zn/Al valance board | 84 | Ft. | 426.56 | 35831.04 | Roof |  | 2 | 39 |  |  | 78
[8 empty] | 1 | 6 |  |  | 6
[12 empty] | 84 | 84
g-03 | Supply and fix 0.47mm Zn/Al gutter | 22 | Ft. | 396.88 | 8731.36
g-04 | Supply and fix 0.47mm Zn/Al bardge flashing and wall flashing | 50 | Ft. | 396.88 | 19844
g-05 | Supply & lay 0.47mm Zn/Al rain water down pipes | 64 | Ft. | 396.88 | 25400.32
| TOTAL FOR ROOF AND ROOF PLUMBING |  |  |  | 846503.72
H | WALL FINISHING AND FLOOR FINISHING WORK
Internal plaster
h-01 | 16mm thick 1:5 cement sand plastering Ground floor | 6.6 | Sqr | 8166.84 | 53901.14 | G/F |  | 1 | 69 |  | 9.5 | 655.5
0
[12 empty] | 655.5 | 6.6
h-02 | 16 mm thick 1:5 cement sand plastering-First floor | 19.8 | Sqr | 8403.56 | 166390.49 | FF |  | 1 | 244 |  | 9.5 | 2318
[8 empty] | -1 | 258.75 |  |  | -258.75
[8 empty] | -1 | 84 |  |  | -84
[12 empty] | 1975.25 | 19.8
h-03 | 16mm thick 1:5 cement sand plastering -2nd floor | 31.8 | Sqr | 8640.28 | 274760.9 | 2/f |  | 1 | 287.5 |  | 12.7 | 3651.25
[8 empty] | -1 | 303.25 |  |  | -303.25
[8 empty] | -1 | 168 |  |  | -168
[12 empty] | 3180 | 31.8
Beam and column plaster
h-04 | 16mm thick 1:5 cement sand plastering - Ground floor | 5 | Sqr | 10060.6 | 50303 | Rent Beam |  | 2 | 192 |  | 0.58 | 222.72
[8 empty] | 1 | 192 | 0.75 |  | 144
[8 empty] | -1 | 31.5 | 1.33 |  | -41.9
[6 empty] | Rent Column |  | 24 | 0.75 |  | 9.5 | 171
[12 empty] | 495.82 | 5
h-05 | 16mm thick 1:5ement sand plastering - First floor | 1.7 | Sqr | 10415.68 | 17706.66 | Rent Beam |  | 2 | 215 |  | 0.58 | 249.4
[8 empty] | -1 | 114 | 1.33 |  | -151.62
0
[6 empty] | Rent Column |  | 10 | 0.75 |  | 9.5 | 71.25
[12 empty] | 169.03 | 1.7
h-06 | 16mm thick 1:5 cement sand plastering-2nd floor | 1 | Sqr | 10652.4 | 10652.4 | Rent Column |  | 10 | 0.75 |  | 12.7 | 95.25
[12 empty] | 95.25 | 1
Revil plaster
h-07 | 16mm thick 1:5 cement sand plastering finishing GF | 40 | Ft | 61.88 | 2475.2 |  |  | 4 | 10 |  |  | 40
[12 empty] | 40 | 0.4
h-08 | 16mm thick 1:5 cement sand plastering - F F | 196 | Ft | 65.31 | 12800.76 |  |  | 1 | 196 |  |  | 196
[12 empty] | 196 | 196
h-09 | 16mm thick 1:5 cement sand plastering 2nd F | 311 | Ft | 68.75 | 21381.25 |  |  | 1 | 311 |  |  | 311
[12 empty] | 311 | 311
Soffit Plastering
h-10 | 16mm thick 1:5 cement sand plastering finishing semirough under faces of slabs- G F floor | 7.1 | Sqr | 7989.3 | 56724.03 | Slab |  | 1 | 702 |  | 1 | 702
[12 empty] | 702 | 7.1
h-11 | 16mm thick 1:5 cement sand soffit plastering finishing semirough on surfaces of slab -First floor | 6.9 | Sqr | 8403.56 | 57984.56 | Slab |  | 1 | 684 |  | 1 | 684
[12 empty] | 684 | 6.9
External plaster
h-18 | 16mm thick 1:5 cement sand plastering finishing semirough on external faces of walls - Ground floor | 4 | M2 | 7279.14 | 29116.56 | Front side |  | 1 | 40 |  | 3 | 120
[8 empty] | 1 | 4 |  | 11 | 44
[6 empty] | Court yard |  | 1 | 11 |  | 3 | 33
[6 empty] | B Wall |  | 2 | 27 |  | 9.5 | 197
[12 empty] | 394 | 4
h-19 | 16 mm thick 1:5 cement sand plastering finishing semirough on external faces of walls -First floor | 4.2 | M2 | 7456.68 | 31318.06 | Front side |  | 1 | 40 |  | 10.5 | 420
[6 empty] | DDT |  | -1 | 250.75 |  | 1 | -250.75
[6 empty] | Court yard |  | 1 | 23 |  | 10.5 | 241.5
[6 empty] | B Wall | [5 empty] | 0
[12 empty] | 410.75 | 4.2
h-20 | 16mm thick 1:5 cement sand plastering finishing semirough on external faces of walls -2nd floor | 5.9 | M2 | 7693.4 | 45391.06 | Front side |  | 1 | 40 |  | 14.5 | 580
[6 empty] | DDT |  | -1 | 273 |  | 1 | -273
[6 empty] | Court yard |  | 1 | 23 |  | 12 | 276
[6 empty] | B Wall | [5 empty] | 0
[12 empty] | 583 | 5.9
Revil plaster
h-21 | 16mm thick 1:5 cement sand plastering finishing semirough on Revils - ground floor | 40 | Ft. | 70.43 | 2817.2 | Front side |  | 1 | 40 |  | 1 | 40
0
0
[12 empty] | 40 | 0.4
[6 empty] | Front side |  | 1 | 79 |  | 1 | 79
0
h-22 | 16mm thick 1:5 cement sand plastering finishing semirough on Revils - F F floor | 79 | Ft. | 73.78 | 5828.62 | [6 empty] | 0
h-23 | 16mm thick 1:5 cement sand plastering finishing semirough on Revils - 2nd floor | 118 | Ft. | 75.46 | 8904.28 | Front side |  | 1 | 118 |  | 1 | 118
0
Plinth Plaster
| 20mm Thick plinth plaster in cement and sand 1:1 finished smooth with neat cement | 2.1 | Sqr | 15268.44 | 32063.72 | Front side |  | 1 | 40 |  | 4 | 160
0
[6 empty] | Court yard | [5 empty] | 0
[6 empty] | B Wall |  | 1 | 27 |  | 1.5 | 40.5
[12 empty] | 200.5 | 2.1
Wall and Floor finishing
Wall tiles
h-24 | Lay 18''x12" wall tiles with tile adasive finish with grouting in toilet walls. PC Rate per tile sqft Rs. 300
| in Ground floor | 0 | Sqr | 55952 | 0 | Front side |  | 1 | 0 |  |  | 0 |  | 250 | 0
0
[6 empty] | Court yard | [5 empty] | 0
[6 empty] | B Wall |  | 1 | 0 |  |  | 0
[12 empty] | 0 | 0
| in first floor | 1.6 | Sqr | 56490 | 90384 | Toilet |  | 2 | 9 |  | 6 | 108 |  | 250 | 4304
[8 empty] | 2 | 5 |  | 6 | 60
[6 empty] | Less door |  | -1 | 2.5 |  | 6 | -15
[9 empty] | 0 |  |  | 0
[12 empty] | 153 | 1.6
| in 2nd floor | 1.6 | Sqr | 56490 | 90384 | Toilet |  | 2 | 9 |  | 6 | 108 |  | 250 | 4304
[8 empty] | 2 | 5 |  | 6 | 60
[6 empty] | Less door |  | -1 | 2.5 |  | 6 | -15
[9 empty] | 0 |  |  | 0
[12 empty] | 153 | 1.6
Floor tiling
To approved design and colour and including 20mm thick cement and sand (1:3) screed bedding level
h-26 | Lay 18"x18" floor tiles with tile adasive finish with grouting. Rate per tile sqft Rs. 260.00
| in Ground floor | 0.3 | Sqr | 51110 | 15333 | Stair landing |  | 2 | 3 | 4 |  | 24 | 0.3 | 180 | 581.04
0
| 4" height skirting | 0 | Ft | 168.66 | 0 | [8 empty] | 180 | 0
| 10" Wide Steps | 53 | Ft | 424.21 | 22483.13 | Stair steps |  | 15 | 3.5 |  |  | 52.5 | 53
| 6" Height Riser | 69 | Ft | 255.55 | 17632.95 | Stair Riser |  | 19 | 3.6 |  |  | 68.4 | 69
| in first floor | 6.4 | Sqr | 51621.1 | 330375.04 |  |  | 1 | 632 |  |  | 632 | 6.4 | 180 | 12395.52
| 4" height skirting | 180 | Ft | 170.35 | 30663 | Skirting |  | 1 | 179.5 |  |  | 179.5 | 180 | 0 | 0
| 10" Wide Steps | 53 | Ft | 428.46 | 22708.38 | Stair steps |  | 15 | 3.5 |  |  | 52.5 | 53
| 6" Height Riser | 69 | Ft | 258.11 | 17809.59 | Stair Riser |  | 19 | 3.6 |  |  | 68.4 | 69
| Pantry worktop | 0.6 | Sqr | 51621.1 | 30972.66 | Floor |  | 1 | 15 |  | 2 | 30
[6 empty] | Wall |  | 1 | 15 |  | 2 | 30
[9 empty] | 0 |  |  | 0
[12 empty] | 60 | 0.6
| in 2nd floor | 6.2 | Sqr | 52137.31 | 323251.32 |  |  | 1 | 620 |  |  | 620 | 6.2 | 180 | 12008.16
| 4" height skirting | 192 | Ft | 172.05 | 33033.6 | Skirting |  | 1 | 192 |  |  | 192 | 192
| 10" Wide Steps | 53 | Ft | 432.74 | 22935.22 | Stair steps |  | 15 | 3.5 |  |  | 52.5 | 53
| 6" Height Riser | 69 | Ft | 260.69 | 17987.61 | Stair Riser |  | 19 | 3.6 |  |  | 68.4 | 69
| Pantry worktop | 0.6 | Sqr | 52137.31 | 31282.39 | Floor |  | 1 | 15 |  | 2 | 30
[6 empty] | Wall |  | 1 | 15 |  | 2 | 30
[9 empty] | 0 |  |  | 0
[12 empty] | 60 | 0.6
| TOTAL FOR WALL FINISHING AND FLOOR FINISHING WORK |  |  |  | 1977755.78
J | PAINTING AND DECORATING
Note - Painting and decorating products shall be CIC applied in accordance with manufacture's recommendations including surface preparation, number of coats and specialized applicators, wall piller used by Asian paints.
Two coat of emulsion paint & one coat acrylic filler & suitable under coat as per manufactuer's instructions to internal plastered walls. Paint shall be used by CIC and wall piller by Asian Paints
j-01 | Internal painting, Ground Floor | 11.6 | Sqr | 6348.4 | 73641.44
j-02 | Internal painting, First Floor | 21.5 | Sqr | 6563.6 | 141117.4
j-03 | Internal painting,2ndFloor | 32.8 | Sqr | 6778.8 | 222344.64
Two coat of emulsion paint & one coat acrylic filler & suitable under coat as per manufactuer's instructions to internal plastered sofits.
j-04 | Sofit painting, Ground floor | 7.1 | Sqr | 6617.4 | 46983.54
j-05 | Sofit painting, First floor | 6.9 | Sqr | 6940.2 | 47887.38
j-06 | Stair Case Ground to 2nd Floor | 1.2 | Sqr | 7155.4 | 8586.48
Two coat of emulsion paint, one coat acrylic filler & two coat of skim coat & suitable under coat as per manufactuer's instructions to internal plastered revils.
j-07 | Internal painting, Ground Floor | 40 | Ft. | 50.3 | 2012
j-08 | Internal painting, First Floor | 196 | Ft. | 53.35 | 10456.6
j-09 | Internal painting, 2ndFloor | 311 | Ft. | 54.88 | 17067.68
Two coat of weather shield paint & one coat of primer under coat paint, as per manufactuer's instructions to external plastered walls.
j-10 | External painting , Ground floor | 4 | Sqr | 7532 | 30128
j-11 | External painting, First Floor | 4.2 | Sqr | 7757.96 | 32583.43
j-12 | External painting, 2nd Floor | 5.9 | Sqr | 7983.92 | 47105.13
Two coat of weather shield paint, one coat of primer & two coat of skim under coat paint, as per manufactuer's instructions to external plastered revils.
j-13 | External painting , Ground floor | 40 | Ft. | 39.63 | 1585.2
j-14 | External painting, First Floor | 79 | Ft. | 42.07 | 3323.53
j-15 | External painting, Loft Floor | 118 | Ft. | 43.29 | 5108.22
| TOTAL FOR PAINTING AND DECORATING |  |  |  | 689930.67
K | ELECTRICAL WORK
k-01 | Lamp point with Switch
Wiring of all lamp points one way or two way including PVC conduit, with 2x1mm2 Cu/PVC/PVC wires and supply and fixing of switches all as show in approved drawings and all materials approved by client.
i | Light Point including external wall light | 28 | nr | 2279 | 63812
ii | Two way light point | 6 | nr | 2915 | 17490
k-02 | Bell push point with Switch
| Wiring of bell push point including PVC conduit, with 2x1mm2 Cu/PVC/PVC wires and supply and fixing of Bell push switched all as show in approved drawings | 2 | nr | 3600 | 7200
k-03 | Fixing of light fittings
fixing of any type of Pendent lamp, Wall lamp, Spot light or any other light fittings complete with screws, anchor bolts, role plugs all materials approved by client. ( cost for fitting Rs: 2500.00)
i | Pendent light | 16 | nr | 3225 | 51600 | [12 empty] | 2500 | 40000
ii | Wall lamp | 6 | nr | 3225 | 19350 | [12 empty] | 2500 | 15000
iii | External Wall lamp | 2 | nr | 3225 | 6450 | [12 empty] | 2500 | 5000
k-04 | Socket outlet(5A/5A W/P/multi Socket)with Wiring
| Wiring of 5A,5A W/P , Multi Socket outlet including PVC conduit, 2x1.5mm2 Cu/PVC/PVC with 2.5mm2 earth wires and supply and fixing of Socket outlet(5A/5A W/P/multi Socket all as show in approved drawings and all materials approved by client. | 0 | nr | 2750 | 0
k-05 | Socket outlet(13A/13A W/P)with Wiring
| Wiring of 13A/13A W/P Socket outlet including PVC conduit, 2x2.5mm2 Cu/PVC/PVC with 2.5mm2 earth wires and supply and fixing of Socket outlet(13A/13A W/P) all as show in approved drawings and all materials approved by client. | 22 | nr | 4187 | 92114
k-06 | Socket outlet(15A/15A W/P)with Wiring
| Wiring of 15A/15A W/P Socket outlet including PVC conduit, 2x2.5mm2 Cu/PVC/PVC with 2.5mm2 earth wires and supply and fixing of Socket outlet(15A/15A W/P) all as show in approved drawings and all materials approved by client. | 4 | nr | 5280 | 21120
k-07 | External garden light
| Wiring of External garden light in two way, including PVC conduit, with 2x1mm2 Cu/PVC/PVC wires and supply and fixing of switches (fixing of switches in house ,location approved by client) including fixing of any type of garden light fitting (cost of the fitting Rs: 5000.00), all as show in approved drawings or instruct by client and all materials approved by client. | 2 | nr | 8670 | 17340 | [12 empty] | 5000 | 10000
k-08 | Telephone/Data/Pro TV Socket outlet with Wiring
| Wiring of Telephone/Data/Pro TV Socket outlet including PVC conduit, 8x0.50mm2 Cu/PVC/PVC 4pair (cat5)cable and supply and fixing of Telephone/Data/Pro TV Socket outlet all as show in approved drawings and all materials approved by client. | 2 | nr | 4800 | 9600
k-09 | TV Socket outlet with Wiring
| Wiring of TV Socket outlet including PVC conduit, RG6 cable and supply and fixing of TV Socket outlet all as show in approved drawings and all materials approved by client. | 4 | nr | 4300 | 17200
k-10 | CCTV system Wiring
| Wiring of CCTV system including PVC conduit,RG6+Hat.twin cable all as show in approved drawings and all materials approved by client. | 2 | nr | 2750 | 5500
k-12 | Main Distribution Unit complete with wiring and testing
Supply and Fixing of Main DB ,including RCCB,MCB,Isolator all as approved by Client ,complete with wiring and testing
1 flush type panel 400x700X125mm
13 MCB SP 10A brand Hanger
03 MCB SP 16A
01 MCB TP 40A
01 MCB 4P 20A
01 MCB 4P 63A
04 RCCB DP 40A 30mA
| Internal wireing and other accessories | 2 | nr | 72500 | 145000
k-14 | Incoming main Cable from CEB meter to main DB
| Supply install & connected 4x16mm2 Cable+ 6mm2 earth cable from Incoming main Cable from CEB meter to main DB including PVC conduit and all materials approved by client. | 90 | Ft. | 950 | 85500
k--20 | Meter box for CEB meter
| Supply and fixing of powder coated metering box wall mounted panel 400x500X200mm flush type | 2 | nr | 8200 | 16400
k-20 | Earth Electrode
| Supply & installation of Earth Electrode (16mm copper bounded)as approved by the Client including 6mm earth wires | 2 | nr | 7200 | 14400
.
k-21 | CEB Power Connection
| Allow Provisional Sum to get the CEB Power connection | item | allow | sum | 45000
| TOTAL FOR ELECTRICAL WORK |  |  |  | 635076
L | PLUMBING WORK
L-02 | Pipe Laying ( For Water Supply)
Supply and install high pressure PVC water supply pipe work with fittings (below ground or above ground) complete with excavation if required or connections, supports and accessries; all in accordance with the drawings and approved by client (rate to include for complete pressure testing)
02. (a) | Using 20mm(1/2") (Type1000) pipes For Water Distribution Inside of the Bath Rooms & others | 45 | Ft | 120.7 | 5431.5
02. (b) | Using 32mm(1") (Type1000) pipes For Water Distribution Inside of the Bath Rooms & others | 30 | Ft | 152.06 | 4561.8
L-04 | Pipe laying (for waste water line)
Supply and PVC waste water line (T - 600 )pipe work with fittings (below ground or above ground) complete with excavation if required or connections, supports and accessries; all in accordance with the drawings and approved by client (rate to include for complete pressure testing)
04. (a) | Using 40mm(1 1/4")(Type600) pipes For Waste water line from wash basin to floor gully | 18 | Ft | 148.44 | 2671.92
04. (b) | Using 63mm(2")(Type600) pipes For Waste Water line from floor gilly to waste water gully, kitchen sink to kitchen gullies. | 32 | Ft | 359.38 | 11500.16
04. (C ) | Using 75mm(2 1/2")(Type600) pipes For Waste water line among kitchen gullies. | 90 | Ft | 515.63 | 46406.7
L-05 | Pipe Laying (For sewerage & Waste Water Lines)
05. (b) | Using 110mm (4")(Type 600) Pipes For Sewerage lines & waste water lines between water closets & man holes, waste water gullies(All pip | 60 | Ft | 609.38 | 36562.8
L-06 | Gullies
06. a) | Sealed gully , (300x300x 300 to 450 deep ) as specified and detailed on drawing (for Waste Water Gullies) (as approved by client) including cover slab | 2 | Nos | 4500 | 9000
06. (b) | Sealed gully , (300x300x 300 to 450 deep ) as specified and detailed on drawing (for Rain Water gullies) (as approved by client) including cover slab | 2 | Nos | 4500 | 9000
06. © | Sealed gully , (300x300x 300 to 450 deep ) as specified and detailed on drawing (for Kitchen Waste Water gullies) (as approved by client) including cover slab. | 1 | Nos | 4500 | 4500
L-07 | Man Holes
07. (a) | Internal size 375mm x 375mm average 450 mm deep to invert, including all associated work all as specified and shown on drawings (as approved by client) including cover slab. | 2 | Nos | 6500 | 13000
L-09 | Water Tank
09. (a) | Supply and Fixing the Plastic Water tank 1500 ltrs including all fitting & accessories | 2 | Nos | 15500 | 31000 | [14 empty] | 101200 | 101200
0
L-10 | Supply and Fixing of Bath Room Fittings / Accessories |  |  |  | 0
| Basin Mixer tap | 2 | Nos | 4950 | 9900 | [14 empty] | 4500 | 9000
| telephone Shower pipe | 2 | Nos | 4500 | 9000 | [14 empty] | 3000 | 6000
10. (e) | Sink Mixer tap | 2 | Nos | 4200 | 8400 | [14 empty] | 12900 | 25800
10. (f) | Bidet Spray | 2 | Nos | 1750 | 3500 | [14 empty] | 1200 | 2400
| 6 pcs. Essentials Accessory Set | 2 | Nos | 4500 | 9000 | [14 empty] | 3000 | 6000
10. (i) | Wash Basin | 2 | Nos | 10150 | 20300 | [14 empty] | 7400 | 14800
10. (j) | Water Closet for servent and driver | 2 | Nos | 17850 | 35700 | [14 empty] | 15100 | 30200
10. (p) | 6x6 Floor Gullies | 2 | Nos | 2450 | 4900 | [14 empty] | 1500 | 3000
| Bath Room Mirror | 2 | Nos | 2500 | 5000 | [14 empty] | 1200 | 2400
10. (s) | Bottle Traps | 4 | Nos | 4250 | 17000 | [14 empty] | 2500 | 10000
10. (t) | gate valve pegler 1" dia | 4 | Nos | 2500 | 10000 | [14 empty] | 2100 | 8400
L-11 | Waste Water, Kitchen waste and Rain water Pit
11. (a) | Supply and placing of precast soakage pit with precast cover slab , Excavation 5ft Dia X 7ft Height for Waste Water Pit with back filling with 3/4" thick metal layer for filter material . As per the approved Location by client.Including laying & connecting the Pipe work inlet & outlet. placing of cover slab and making slab opening in 450X450 size brick wall up to finish floor level with smooth plaster for covering around the opening and placing concrete cover slab for top cover all as approved by Client | 3 | Nos | 53130 | 159390
L-15 | Septic Tank with Soakage Pit
15. (a) | Supply and placing of precast Precast Septic Tank 8'X3' dia and soakage pit with cover slab 3' dia Excavation 9'x4'x5'for Septic Tank & 4ft Dia X 7ft Height for Soakage pit. Including 6" thick sand Bed for Septic Tank. Placing of Precast Septic Tank back filling with approved available soil. and soakage pit back filling with 3/4" thick metal layer for filter material . As per the approved Location by Client.Including , laying & connecting the Pipe work inlet & outlets. placing of cover slab and making slab opening in 450X450 size brick wall up to finish floor level with smooth plaster for covering around the opening and placing concrete cover slab for top cover all as approved by Client | 2 | Nos | 75700 | 151400
| TOTAL FOR PLUMBING WORK |  |  |  | 617124.88
N | DOORS AND WINDOWS
GROUND, FIRST FLOOR AND SECOND FLOOR
TIMBER DOORS
| Door type D2, size 3'-6" X 8'-0" high, Solid timber panelled Single Sash Door . As per detail drawing. Rate shall include for locks and all necessary ironmongery, and all as per detail drawings and specifications. | 7 | Nos. | 50400 | 352800
| Door type D3, size 2'-9" X 8'-0" high, Solid timber panelled Single Sash Door . As per detail drawing. Rate shall include for locks and all necessary ironmongery, and all as per detail drawings and specifications. | 2 | Nos. | 39600 | 79200
ALUMINIUM GLAZED DOORS AND WINDOWS
Powder coated approved colour aluminium framed doors, windows units consisting of aluminium frames, transoms, mullians, aluminium framed glazed panels, aluminium louvered panels including necessary hardware such as hinges, floor hinges, fasteners, stays, bolts, locks, handles and the like all as detail drawing, iron mongery schedule and specification.
| Single sash sliding Door type SD4, size 9'-10"x 8'-0" high overall aluminium framed glazed door and fixed glass window as per detail drawing. | 1 | Nos. | 149416 | 149416
| Single sash sliding Door type SD5, size 10'-4"x 8'-0" high overall aluminium framed glazed door and fixed glass window as per detail drawing. | 1 | Nos. | 157016 | 157016
| Two sash sliding WIndoor type SW3, size 7'-6"x 8'-0" high overall aluminium framed glazed window as per detail drawing. | 1 | Nos. | 114000 | 114000
| Two sash sliding WIndoor type SW4, size 7'-0"x 8'-0" high overall aluminium framed glazed window as per detail drawing. | 3 | Nos. | 106400 | 319200
| Two sash sliding WIndoor type SW5, size 5'-0"x 4'-9" high overall aluminium framed glazed window as per detail drawing. | 2 | Nos. | 45125 | 90250
| Two sash sliding WIndoor type SW6, size 6'-0"x 5'-0" high overall aluminium framed glazed window as per detail drawing. | 1 | Nos. | 57000 | 57000
| Fixed Glass WIndoor type FG1, size 4'-0"x 5'-0" high overall aluminium framed glazed window as per detail drawing. | 2 | Nos. | 34000 | 68000
| Fixed Glass WIndoor type F3, size 2'-6"x 3'-0" high overall aluminium framed glazed window as per detail drawing. | 2 | Nos. | 12750 | 25500
ROLLER DOOR
| Roller door type RD1, size 35'-0' x 8'-0" high overall roller door with powder coated aluminium box cover as per detail drawing. | 1 | Nos. | 392000 | 392000
| TOTAL FOR TIMBER DECORATIONS |  |  |  | 1804382
METAL WORK
STAIRCASE HANDRAIL
| 3'-0" high hand rails consisting of 2" diameter Epoxy painted MS top rail, 1.5" diameter MS verticals and 0.5" diameter MS internal horizontal rails including necessary fixing methods as per detail drawings. | 45 | Ft. | 3062.5 | 137812.5
GRILL WORK
| Fabricate and fixing Grill Work Type GW1 size 38'-7" x 9'-0" of Epoxy painted 4"x 2" Box Iron frame work with 2"x 2" box iron verticals fix to frame. | 1 | No. | 62499.6 | 62499.6
| Fabricate and fixing Grill Work Type GW1 size 38'-7" x 13'-9" of Epoxy painted 4"x 2" Box Iron frame work with 2"x 2" box iron verticals fix to frame. | 1 | No. | 95485.5 | 95485.5
295797.6
[15 empty] | 33592.72 |  | 0 |  | 70000 |  | 219200